## Cost estimate history
	2559.00949655172	3308.19012068966	29.28%

	2352.11294482759	3101.29356896552

	682112.754	899375.135	31.85%	Half can be explained by general build price inflation past eighteen months, other half by spec upgrades
	600980.4	792401
	2022-10-10	2024-04-14
Foundations main house	47296	60980	28.93%	General build price inflation + concrete levy
Timberframe main house	138169	277531	100.86%	42% can be explained by better u-values and build price inflation (wall and roof u-values improved by 18.75%); Use of outer rather than inner stud thermal break
Outer block leaf excluding render	17486.4	21858	25.00%	General build price inflation + concrete levy
Stairs	15000	15000	0.00%
Doors	17750	21935	23.58%	15% of this should be general build price inflation, not sure why rest
Window boards	928	2054	121.34%	Much better insulating reveals that before
Skirting	3540	3540	0.00%
Glazing	53000	47599	-10.19%	Nordan quote lower than expected (will likely rise next quote)
Rooflights	27993	27993	0.00%
Outer render and cladding	50775	51275	0.98%
Internal plasterboard and tiling excluding finish	46231	53637	16.02%	General build price inflation
Internal floor finishes	26625	26625	0.00%
Internal plasterboard finishes	16633	31332	88.37%	General build price inflation + concrete levy
Roof tiles, facia and soffit	28607	32543	13.76%	General build price inflation
Roof gutters and drainpipes	7196	7752	7.73%	General build price inflation
Interior painting	12861	14063	9.35%	General build price inflation
Kitchen	8000	8000	0.00%
Wardrobes	1500	1500	0.00%
Cloaks etc	1000	1000	0.00%
Plumbing and tanking	14000	14000	0.00%
Ventilation	8500	9000	5.88%
Bathrooms	3000	3000	0.00%
Sprinkler	10595	10595	0.00%
Misc assoc	1400	1400	0.00%
RECI electrical wiring	20840	25000	19.96%	General build price inflation + electrician shortage
Waste disposal	9000	9000	0.00%
Foul and stormwater	13055	14189	8.69%	General build price inflation

## 202404
792401	899375.135	Main house
48240	54752.4	Greenhouse
44052.8634361234	50000	Outhouse

	56672
	2833
	300
	525
60980	650	Foundations main house

	257391
	12869
	2919
	1914
	1484
277531	954	Timberframe main house

	826
	14616
	2262
	715
	585
	348
	2242
	240
21858	24	Outer block leaf excluding render

	15000	Stairs
	21935	Doors
	2054	Window boards
42529	3540	Skirting

	41174
	2500
	3000
47599	925	Glazing

	21494
	1092
	2360
	2398
27993	649	Rooflights

	25240
	4889
	1514
	3888
	3426
	1425
	1372
	888
	7525
	768
	116
	112
51275	112	Outer render and cladding

	12528
	2794
	19890
	960
	1486
	10459
53637	5520	Internal plasterboard and tiling excluding finish

	12484
	12386
26625	1755	Internal floor finishes

	15840
	22
	2673
	2128
	10614
31332	55	Internal plasterboard finishes

	15245
	583
	425
	300
	840
	3770
	455
	2000
	450
	2875
	2730
	780
	1925
32543	165	Roof tiles, facia and soffit

	3234
	294
	200
	34
	2700
	420
	420
7752	450	Roof gutters and drainpipes

	130
	1327
	445
	891
	6840
	635
14063	3795	Interior painting

	8000	Kitchen
	1500	Wardrobes
	1000	Cloaks etc

	14000	Plumbing and tanking
	9000	Ventilation
	3000	Bathrooms
	10595	Sprinkler
	1400	Misc assoc

	25000	RECI electrical wiring

82495	9000	Waste disposal

	2106
	930
	950
	165
	200
	400
	3388
	1085
	550
	1000
	720
	1845
	450
14189	400	Foul and stormwater

## 202210
583494	662265.69	Main house
48240	54752.4	Greenhouse
44052.8634361234	50000	Outhouse

47296		Foundations main house

138169		Timberframe main house

		Outer block leaf excluding render

	15000	Stairs
	17750	Doors
	928	Window boards
37218	3540	Skirting

	50000
53000	3000	Glazing

	21494
	1092
	2360
	2398
27993	649	Rooflights

	25240
	4889
	1514
	3888
	3426
	1425
	1372
	888
	7025
	768
	116
	112
50775	112	Outer render and cladding

	26816
	2286
	1150
	10459
46231	5520	Internal plasterboard and tiling excluding finish

	12484
	12386
26625	1755	Internal floor finishes

	11040
	5520
16633	73	Internal plasterboard finishes

	13229
	605
	425
	300
	868
	4160
	455
	2000
	450
	2875
	2520
28607	720	Roof tiles, facia and soffit

	3038
	245
	200
	28
	2610
	350
	350
7196	375	Roof gutters and drainpipes

	130
	1327
	445
	891
	6156
	635
12861	3277	Interior painting

	8000	Kitchen
	1500	Wardrobes
	1000	Cloaks etc

	14000	Plumbing and tanking
	8500	Ventilation
	3000	Bathrooms
	10595	Sprinkler
	1400	Misc assoc

	20840	RECI electrical wiring

77835	9000	Waste disposal

	1898
	450
	675
	950
	165
	200
	3102
	450
	810
	440
	900
	720
	1845
13055	450	Foul and stormwater